## Time Log
Time Log
Wall-clock ~10h (multitasking across other work). Durations below are focused-effort estimates derived from git commit timestamps, normalized to the ~10h total.
Date | Hrs | Area | AI tool | Commit | What AI generated | What I changed / overrode
06-14 | 0.5 | Project scaffold | Claude Code | 474e608 | Dockerfile, compose, /health | conventions tightened
06-14 | 0.75 | DB schema / DuckDB | Claude Code | 2c08d1b | Star schema, views, macros | grain/SCD2 corrections
06-15 | 0.75 | LLM insight layer | Claude Code | 14258d2 | Ollama NL→SQL /insight | SQL guardrails added
06-15 | 0.75 | Streamlit UI + auto-load | Claude Code | fa98265 | UI + docker_init.py | layout/copy edits
06-15 | 0.25 | UI polish | Claude Code | 2c41dcd | styling tweaks | manual
06-20 | 0.75 | Forecast model (XGBoost) | Claude Code | 04700b7 | XGBoost model + endpoints | later replaced by SARIMA
06-20 | 1.5 | Medallion ETL | Claude Code | fd61c1d | Bronze→Silver→Gold + tests | fixed ETL not spawning in Docker; removed fossil code
06-21 | 0.75 | Forecast model (SARIMA) | Claude Code | c80bfca | SARIMA model, API, UI | swapped out XGBoost approach
06-21 | 0.75 | Report API + charts + tests | Claude Code | 121e1bb | endpoints, Plotly, api_tests/ | de-hardcoded inputs
06-21 | 0.5 | CI pipeline | Claude Code | c70d9d6 | GH Actions lint/test/build | removed dead imports
06-21 | 1.25 | Revenue forecast + report UI + README | Claude Code | 6b8125a | endpoint, UI, README | parameterized, content edits
06-22 | 0.25 | PR-review automation | Claude Code | 74ee5ed | reviewdog workflow | —
06-22 | 0.25 | CI fix | Claude Code | 74ba9a4 | — | overrode AI: non-existent reviewdog/action-ruff → ruff rdjson pipe
06-22 | 0.25 | ADRs | Claude Code | 8107ae5 | 4 ADRs | —
06-22 | 0.5 | Arch diagram + handoff docs | Claude Code | fdf1e7d | logical .drawio/.png, CI/CD notes | —
06-22 | 0.25 | README streamline | Claude Code | a2fb87e | — | manual
TOTAL | 10

## Tool Usage Summary
Tool Usage Summary
Field | Value
Total time | ~10h (wall-clock, multitasking)
Time split | ETL/data ~35%, models ~20%, API/UI ~25%, infra/CI/docs ~20%
Primary AI tool | Claude Code (Opus 4.x), plan mode
% AI-generated (initial) | ~96%
% modified / overridden | ~5%
Biggest AI win | Rapid scaffolding of the medallion ETL + star schema + report endpoints (thousands of usable LOC)
Biggest AI miss | Container orchestration — ETL service built but never spawned/ran under Docker; plus pervasive hardcoding in the API layer

## Decision Log
Decision Log
Decision | Options considered | Chosen | Why chosen | AI's suggestion | Followed?
Analytical store | DuckDB vs Postgres/cloud DW | DuckDB + star schema (ADR-001) | Embedded, zero-ops OLAP on a single file; fast analytics with no server to manage — fits a local/skeleton project | DuckDB | Yes
ETL architecture | Single-stage vs layered | Medallion, declarative multi-format (ADR-002) | Separates raw/clean/curated, enables validation + quarantine, and multi-format ingestion via declarative adapters | Medallion | Yes
Forecasting model | XGBoost vs SARIMA | SARIMA (ADR-003) | Captures revenue seasonality better than a tree model on limited synthetic history; interpretable | XGBoost first, then SARIMA | Overrode — built XGBoost, switched to SARIMA for seasonality
LLM hosting | Cloud API vs local | Ollama qwen2.5:7b local (ADR-004) | No API keys/cost, runs offline in-container, data stays local — ideal for an evaluator cloning fresh | Ollama local | Yes
Business UI | Streamlit vs custom FE | Streamlit | Fastest path to a business-user UI in pure Python; no separate frontend stack | Streamlit | Yes
ETL execution in Docker | Auto-run vs non-spawning service | Rewired so pipeline runs on compose | A reviewer cloning fresh must get a running pipeline; a non-spawning service is a broken deliverable | AI left service non-spawning | Overrode — rewired ETL service
CI lint integration | reviewdog/action-ruff vs pipe | ruff rdjson piped to reviewdog | The AI-suggested action does not exist; the rdjson pipe is the working equivalent | non-existent action | Overrode

## Pod Plan
Pod Plan
Phase 0 (shared, before parallelization): 1) Scoping 2) High-level design of the end-to-end flow 3) Define data contracts between systems 4) Generate mock data from contracts and load into the DB 5) Once mock data exists, each pod works independently against the contracts.
Engineer | Workstream | ADR owner | Dependencies | Acceptance criteria | Handoff classification
A — ETL & Data Foundation | WS1 Data foundation & contracts: schema (etl/sql/init.sql), dimensions, mock-data seed | ADR-001 | none | Contracts published; mock data loads clean | Production-ready
A — ETL & Data Foundation | WS2 ETL medallion pipeline (etl/) | ADR-002 | WS1 | Data populated at correct grain; historical + monthly loads; pipeline trigger updates models; audit tables generated; validation runs; aggregated views available; Gold has no invalid data | Needs hardening (no scheduler — manual trigger; single-writer lock)
B — Models & Insight | WS3 Forecasting models: SARIMA + demand (decision-tree), retrained within ETL and verified under Docker | ADR-003 | WS2 Gold tables | Forecasts produced per category/region; retrain fires on pipeline run | Prototype
B — Models & Insight | WS4 LLM insight: Ollama container LLM, NL→SQL served as insight endpoint | ADR-004 | WS1 schema context | NL question returns validated SQL result | Prototype (guardrails added)
C — API & UI | WS5 API layer: APIs over ETL views; forecast-trigger API with params; insight API (NL→SQL→execute→output) | (future API ADR) | WS2 / WS3 / WS4 | Endpoints return contract-valid responses; no hardcoded values | Needs hardening (de-hardcode)
C — API & UI | WS6 UI layer: insight UI from insight API; report tab from forecast APIs | — | WS5 | Insight + report tabs render live data | Prototype

## Coaching Moments
Coaching Moments
A. How I work with AI (method I'd teach an engineer)
• Plan-first, never auto-accept. Drive with plan mode to pin down requirements before any code is written. Never use auto-update; approve changes incrementally so each is refined over several passes before it lands. The codebase reflects intended design, not the model's first draft.
• Manage context deliberately. Start a fresh chat and /compact for each new module or distinctly new functionality, so tokens stay bounded and context stays crisp — keeps the model from drifting on long sessions.
• Incremental, test-as-you-go escalation. Build the smallest well-defined unit, test it thoroughly by hand, then add complexity one step at a time. Each layer is verified before the next, which also surfaces unknowns early.
B. What I coach engineers to give the AI up front
• File segregation & project scope. State where files belong and the project conventions up front (e.g., the md/ docs convention, "everything must run in a container," expected file formats). If scope/conventions aren't stated, the AI won't honor them.
C. Where the AI failed → what I changed → what I'd teach
What AI generated | What I changed | What I'd teach
ETL service that built but never spawned/ran under Docker | Rewired the ETL service so the pipeline runs on compose up | AI reasons about code, not runtime orchestration — verify services actually run in the container, not just that images build
Fossil/older code left after ETL files changed | Removed dead/duplicate code paths | AI appends and rarely deletes — review refactors for orphaned logic
Incorrect data-population logic | Corrected how data lands at the right grain | Data grain/population rules must be human-specified
Incorrect data flow through the model layer | Fixed model input/feature flow | Model data contracts need explicit definition
Pervasive hardcoded values once API endpoints were generated | Parameterized inputs/config | AI defaults to hardcoding — insist on params/config and hunt magic values